## Projects
ID | Project | budget_USD | execution_rate | date_start | date_up_todate | date_end | Months | monthly_spend_all | active_0 | active_1 | active_2 | Districts_RHC | districts_number | perc_subcounties | Prop_district_school_level | Spendprop_Distlevel_all | Spendprop_Nat_all | Spendprop_RHC_all | A_erp | erp_relevant_prop | sum_outcomes_raw | sum_programme_raw | sum_activity_raw | donor_summary
88734000000030041 | various 2020 | 12407000 | 0.4 | 2020-01-01 | 2020-07-30 | 2020-12-31 | 6.94 | 720461.0625 |  |  | 6 | 7 | 8 | 1 | 0.98 | 0.8575 | 0.02 | 0.8775 | 0.99 | 0.01 | 1 | 1 | 1 | Combination
88734000000032089 | Support Skilling Uganda/ SSU | 32584270 | 0.81 | 2016-07-01 | 2020-06-30 | 2021-07-01 | 48 | 550093.625 | 12 | 12 | 12 | 6 | 20 | 1 | 0.8 | 0.24 | 0.2 | 0.44 | 0.25 | 0 | 1 | 1 | 1 | Combination
88734000000035013 | Right to Learn – Improving access to and quality of education in Palabek Refugee Settlement | 563221 | 0 | 2019-01-01 |  | 2021-12-31 |  |  |  | 5.9 | 12 | 1 | 2 | 1 | 1 | 0.5 |  | 0.5 | 1 |  | 0.34 | 1 | 0.08 | Multi-lateral
88734000000036009 | Secondary and Vocational Education Management in West Nile (Adjumani) | 459519 | 0.98 | 2018-01-01 | 2018-01-31 | 2018-01-31 | 0.99 | 456420.2188 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000036019 | Secondary and Vocational Education Management in West Nile (Adjumani) | 595815.25 | 1 | 2019-01-01 | 2019-01-31 | 2019-01-31 | 0.99 | 601833.5625 |  | 7 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 0.93 | Multi-lateral
88734000000036033 | Adjumani Education Project | 112359.5469 | 1.02 | 2018-01-01 | 2018-01-31 | 2018-01-31 | 0.99 | 115652.1484 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 0.9 | 1 | 1 | Private donors
88734000000036043 | Adjumani Education Program | 86945 | 0.98 | 2018-01-01 | 2018-12-31 | 2018-12-31 | 11.97 | 7090.5195 | 5.9 | 6 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 0.54 | 1 | 0.62 | Private donors
88734000000036053 | Adjumani Education Program | 146067.4219 | 0.48 | 2019-10-01 | 2019-12-31 | 2020-12-31 | 2.99 | 23252.1523 |  |  | 9 | 2 | 2 | 1 | 1 | 1 |  | 1 | 1 | 0 | 0.77 | 1 | 0.82 | Bilateral
88734000000036063 | Adjumani Education Program | 76586 | 1.03 | 2019-01-01 | 2019-12-31 | 2019-12-31 | 11.97 | 6601.6445 |  | 5.9 | 6 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 0.97 | Private donors
88734000000036073 | Urban Program Kampala | 75612 | 1 | 2018-01-01 | 2018-12-31 | 2018-12-31 | 11.97 | 6316.792 | 5.9 | 6 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.7 | 0.3 | 1 | 1 | 0.73 | Bilateral
88734000000036083 | Urban Program Kampala | 68337.0781 | 1.02 | 2018-01-01 | 2018-12-31 | 2018-12-31 | 11.97 | 5817.564 | 5.9 | 6 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 0.9 | 1 | 0.94 | Private donors
88734000000036093 | Urban Program Kampala | 55397 | 1.03 | 2019-01-01 | 2019-12-31 | 2019-12-31 | 11.97 | 4775.1714 |  | 5.9 | 6 | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.8 | 0.2 | 0.9 | 1 | 0.42 | Bilateral
88734000000036103 | Urban Program Kampala | 109710 | 1.03 | 2019-01-01 | 2019-12-31 | 2019-12-31 | 11.97 | 9456.9033 |  | 5.9 | 6 | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.8 | 0.2 | 1 | 1 | 0.89 | Private donors
88734000000037009 | Innovative and Inclusive Accelerated Education Programme for refugee and Host community Children (INCLUDE) | 3771996.75 | 0 | 2018-04-04 | 2020-12-31 | 2020-12-31 | 32.94 | 17.5153 | 2.9 | 12 | 12 | 3 | 3 | 0.75 | 0.15 | 0.1125 | 0.05 | 0.1625 | 0.41 | 0.41 | 1 | 1 | 1 | Bilateral
88734000000037019 | Education Support for Refugee and Host Community Children and adolescents in Bidi Bidi Settlement, Yumbe district and Rhino Camp settlement, Arua District. | 390042.0625 | 0.47 | 2020-01-01 | 2020-12-31 | 2020-12-31 | 12 | 15162.3076 |  |  | 6 | 2 | 2 | 1 | 0.95 | 0.95 | 0.05 | 1 | 0.48 | 1 | 1 | 1 | 1 | Multi-lateral
88734000000037025 | Consortium project for Vocational Skill training & AEP in Kyangwali DRC refugees and Host communities |  |  | 2019-10-01 | 2022-09-30 | 2022-09-30 | 36 | 19.3034 |  |  | 9 | 1 | 1 | 0.75 | 0.95 | 0.7125 | 0.05 | 0.7625 | 0.34 |  | 1 | 1 | 1
88734000000038025 | Strengthening Education Systems for Improved Learning (SESIL) | 39577836 | 0.42 | 2018-01-01 | 2020-07-31 | 2022-07-01 | 30.97 | 539037.4375 | 5.9 | 12 | 12 | 6 | 27 | 0.5 | 0.7 | 0.077778 | 0.3 | 0.37778 | 0.1 | 0 | 1 | 1 | 1 | Bilateral
88734000000039009 | Holistic Community Development (HCD) | 1696972 | 0.4 | 2019-10-01 | 2020-08-28 | 2023-09-30 | 10.92 | 62160.1641 |  |  | 9 | 1 | 1 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.09 | 0.06 | 1 | 1 | 0.94 | Private donors
88734000000039023 | Ayiri, Children and Youth for community Change | 2248155 | 0.1 | 2019-07-01 | 2020-07-30 | 2028-06-30 | 12.99 | 17775.9824 |  |  | 12 | 1 | 1 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.15 |  | 1 | 1 | 1 | Private donors
88734000000040153 | USAID/Uganda Literacy Achievement and Retention Activity | 45618976 | 0.85 | 2015-04-07 | 2020-06-30 | 2021-04-06 | 62.83 | 613635.8125 | 12 | 12 | 12 | 3 | 43 | 0.25 | 0.85 | 0.014826 | 0.15 | 0.16483 | 0.07 | 0.93 | 1 | 1 | 1 | Combination
88734000000040163 | Education Infrastructure Enhancement for South Sudanese Refugees and Host Communities in Bidibidi | 4407792 | 0.57 | 2017-12-01 | 2020-07-31 | 2020-11-30 | 31.99 | 78620.3203 | 6.9 | 12 | 12 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000041009 | Support Program to the Refugee Settlements and Host Communities in Northern Uganda (SPRS-NU) | 3414774.25 | 0.99 | 2016-08-30 | 2020-07-31 | 2020-08-30 | 47.05 | 72084.9922 | 12 | 12 | 12 | 4 | 4 | 1 | 0.98 | 0.98 | 0.02 | 1 | 0.6 | 0.4 | 1 | 1 | 1 | Bilateral
88734000000041039 | Innovative and Inclusive Accelerated Education Programme for Refugee and Host Community Children (INCLUDE) | 16922608 | 0.54 | 2018-02-01 | 2020-07-31 | 2020-12-31 | 29.95 | 305743.2188 | 4.9 | 12 | 12 | 6 | 6 | 1 | 0.99 | 0.99 | 0.01 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000042073 | Education Cannot Wait (ECW) Programme, Uganda | 21194416 | 0.66 | 2018-09-01 | 2020-07-31 | 2021-12-31 | 22.98 | 605659.4375 |  | 9.9 | 12 | 10 | 10 | 1 | 0.95 | 0.95 | 0.05 | 1 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000043013 | Strengthening Access to Inclusive Quality EiE for Congolese and South-Sudanese Refugee and Host Community Children in Kyaka II refugee settlement in Kyegegwa District, and in Yumbe and Adjumani Districts in Southwestern and West Nile Regions, Uganda | 1123595.5 | 0.05 | 2020-04-01 | 2020-06-30 | 2021-03-31 | 2.96 | 18979.6523 |  |  | 3 | 3 | 3 | 1 | 0.95 | 0.95 | 0.05 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000043019 | Enhancing support to vulnerable refugee and host communities in West Nile | 105436.8594 | 1 | 2019-01-01 | 2020-03-31 | 2019-12-31 | 14.96 | 7047.9185 |  | 5.9 | 6 | 3 | 2 | 1 | 0.95 | 1.425 | 0.05 | 1.475 | 0.35 | 0 | 0.65 | 1 | 1
88734000000044021 | WHIRS (Water and Hygiene in Imvepi Refugee Settlement) BPRM | 1499965 | 1 | 2018-09-15 | 2018-11-14 | 2018-11-14 | 1.97 | 761403.5625 |  | 4.5 |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0.16 | 0 | 1 | 1 | 1 | Bilateral
88734000000044035 | Teach Me More II | 156369.6562 | 0.95 | 2017-04-01 | 2018-03-31 | 2018-03-31 | 11.97 | 12387.8975 | 2.9 |  |  | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 0.44 | 0.56 | 1 | 1 | 1 | Private donors
88734000000044045 | RISE | 337078.6562 | 0.26 | 2020-01-01 | 2021-07-31 | 2021-12-31 | 18.97 | 4671.3027 |  |  | 6 | 3 | 3 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Private donors
88734000000044055 | COVID-19 Education Response II | 112359.5469 | 0 | 2020-08-01 | 2020-08-01 | 2020-12-31 | 0 |  |  |  |  | 2 | 2 | 0.25 | 1 | 0.25 | 0 | 0.25 | 0 | 1 | 0 | 1 | 0 | Private donors
88734000000044073 | PlayMatters - Sparking Lifelong Learning | 12246492 | 0.03 | 2020-01-01 | 2020-06-30 | 2024-12-31 | 5.95 | 67939.5 |  |  | 6 | 2 | 2 | 1 | 0.2 | 0.2 | 0.8 | 1 | 1 | 0 | 1 | 1 | 1 | Foundation
88734000000045097 | Support Program to the Refugee Settlements and Host Communities in Northern Uganda (SPRS –NU) | 5505618 | 0.73 | 2016-07-01 | 2020-06-30 | 2020-12-30 | 48 | 84241.3984 | 12 | 12 | 12 | 4 | 4 | 0.75 | 1 | 0.75 |  | 0.75 | 1 |  | 1 | 1 | 1 | Bilateral
88734000000045175 | Support to Skilling Uganda (SSU) – Northern Uganda | 2915377.5 | 0.28 | 2019-05-01 | 2020-06-30 | 2021-06-30 | 14.01 | 58911.7852 |  | 2 | 12 | 3 | 4 | 0.75 | 1 | 0.5625 |  | 0.5625 | 1 |  | 1 | 1 | 1 | Bilateral
88734000000045197 | Education Assistance for Congolese in Refugee Settlements, Western Uganda | 517451 | 1.01 | 2020-04-01 | 2020-08-21 | 2020-12-31 | 4.67 | 112014.1719 |  |  | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000046009 | CARE International in Uganda | 600494 | 1 | 2018-01-01 | 2020-08-21 | 2020-12-31 | 31.66 | 18947.1895 | 5.9 | 12 | 12 | 5 | 8 | 1 | 0.8 | 0.5 | 0.2 | 0.7 | 0.7 | 0.3 | 1 | 1 | 1 | Multi-lateral
88734000000046019 | Construction of Schools for South Sudanese Refugees in Uganda | 464000 | 1 | 2018-01-01 | 2019-02-28 | 2018-12-31 | 13.91 | 33357.2969 | 5.9 | 6 |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Private donors
88734000000046029 | S. Sudanese Refugee Response: Education Infrastructure in Northern Uganda | 300000 | 1 | 2018-01-01 | 2019-05-31 | 2019-03-29 | 16.93 | 17720.0234 | 5.9 | 8.9 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | Private donors
88734000000046039 | Education Cannot Wait (ECW) - Access to Education for all | 3265638 | 0.46 | 2018-11-15 | 2020-08-15 | 2020-12-31 | 21.01 | 71673.1094 |  | 7.5 | 12 | 3 | 3 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000046049 | EDUCATION INFRASTRUCTURE FOR CONGOLESE REFUGEES AND HOST COMMUNITIES IN SOUTHWESTERN UGANDA | 600000 | 1 | 2019-06-17 | 2020-08-15 | 2020-08-31 | 13.97 | 42949.1758 |  | 0.4 | 12 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | Private donors
88734000000048013 | Integrating Urban Refugees and Asylum Seekers through Protection and Empowerment | 230898.875 | 0.37 | 2018-11-01 | 2020-08-21 | 2021-11-30 | 21.67 | 3914.6958 |  | 7.9 | 12 | 1 | 4 | 1 | 1 | 0.25 |  | 0.25 | 0.06 |  | 0.06 | 0.06 | 1 | Private donors
88734000000049011 | Adolescent Development Programme for Karamoja, Eastern and West Nile region | 655317 | 1 | 2018-01-01 | 2020-08-25 | 2020-12-31 | 31.79 | 20613.9355 | 5.9 | 12 | 12 | 4 | 4 | 0.5 | 1 | 0.5 |  | 0.5 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000050013 | Education Assistance for South Sudanese in Refugee Settlements, Northern Uganda (4) | 1012200 | 1 | 2018-08-01 | 2019-05-15 | 2019-05-15 | 9.44 | 107224.5781 |  | 10.5 |  | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050023 | Education Assistance for South Sudanese in Refugee Settlements, Northern Uganda (5) | 979461 | 1 | 2019-05-15 | 2020-03-30 | 2020-03-30 | 10.52 | 93104.6562 |  | 1.5 | 9 | 3 | 3 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050037 | Education Assistance for South Sudanese in Refugee Settlements, Northern Uganda (5+) | 280000 | 1 | 2019-11-01 | 2020-02-29 | 2020-02-29 | 3.95 | 70692.3984 |  |  | 8 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050055 | Education Assistance for South Sudanese in Refugee Settlements, Northern Uganda (6) | 316322 | 0.6 | 2020-03-31 | 2020-07-31 | 2020-12-31 | 4.01 | 47244.1367 |  |  | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | Combination
88734000000050065 | MFA 2019-2020 | 674157.3125 | 1 | 2019-04-01 | 2020-05-31 | 2020-05-31 | 14.01 | 48119.7227 |  | 3 | 11 | 2 | 2 | 1 | 0.95 | 0.95 | 0.05 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050075 | MFA 2018-2019 | 752809 | 1 | 2018-04-01 | 2019-03-31 | 2019-03-31 | 11.97 | 62891.3086 | 3 | 9 |  | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050085 | MFA 2017-2018 EiE Assistance to South Sudanese refugee children in Pagrinya and Bidibidi refugee settlements in West Nile Region, Uganda | 786516.875 | 1 | 2017-04-01 | 2018-03-31 | 2018-03-31 | 11.97 | 65707.3359 | 2.9 |  |  | 2 | 2 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050099 | LEARN — Lasting Education Achievements Responding to Needs | 2000000 | 1 | 2019-09-01 | 2020-07-31 | 2020-08-31 | 10.98 | 182149.375 |  |  | 10 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000050121 | Uganda Teacher and School Effectivnes Project | 100000000 | 0.98 | 2015-07-01 | 2020-07-31 | 2020-03-31 | 61.05 | 1612941.5 | 12 | 12 | 9 | 13 | 120 | 0.25 | 0.84 | 0.02275 | 0.16 | 0.18275 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000051009 | Education Assistance for South Sudanese in Refugee Settlements, Northern Uganda (3) | 1643201 | 1 | 2017-06-01 | 2018-07-31 | 2018-05-31 | 13.97 | 117300.8594 | 4.9 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral
88734000000051023 | Education Management for Primary, Secondary and Vocational skills training for Refugees residing in Settlements (Palorinya & Obongi / Kyaka II / Rwamwanja / Bidibidi). | 2916754 | 0.51 | 2020-01-01 | 2020-06-30 | 2020-12-31 | 5.95 | 252100.8438 |  |  | 6 | 4 | 4 | 1 | 0.95 | 0.95 | 0.05 | 1 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000051037 | Education Management for Primary, Secondary and Vocational skills training in Bidibidi, Palorinya, Kyaka and Rwamwanja Refugee Settlements. | 4142113 | 1 | 2019-01-01 | 2019-12-31 | 2019-12-31 | 11.97 | 346041.1875 |  | 5.9 | 6 | 4 | 4 | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000051051 | Access and quality education for primary, secondary and TVET learners in Bidibidi, Omugo, Rwamwanja and Palorinya settlements | 1908440 | 1 | 2018-01-01 | 2018-12-31 | 2018-12-31 | 11.97 | 159435.25 | 5.9 | 6 |  | 4 | 4 | 1 | 1 | 1 |  | 1 | 0.99 | 0.01 | 1 | 0.99 | 1 | Multi-lateral
88734000000051085 | Play Matters | 511990 | 0.22 | 2020-02-01 | 2020-07-31 | 2025-08-31 | 5.95 | 19050.084 |  |  | 4.9 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | Private donors
88734000000052009 | Emergency intervention to South Sudanese refugees and host communities in West Nile - Uganda, through coordinated and appropriate WASH and education services and resources to rebuild livelihoods | 424526.9688 | 0.92 | 2017-05-01 | 2019-01-01 | 2018-10-31 | 20.05 | 19552.0371 | 12 | 4 |  | 3 | 3 | 1 | 1 | 1 | 0 | 1 | 0.93 | 0.02 | 1 | 1 | 0.98 | Bilateral
88734000000054045 | USAID-Uganda School Health and Reading Program (SHRP) | 70510488 | 0.99 | 2012-05-21 | 2019-08-20 | 2019-08-20 | 87.02 | 805886.5 | 12 | 12 | 1.6 | 2 | 43 | 0.25 | 0.85 | 0.0098837 | 0.15 | 0.15988 | 0.05 | 0.95 | 1 | 1 | 1 | Combination
88734000000055053 | Partnership for Improving Prospects | 48775784 | 0.23 | 2019-07-01 | 2020-06-30 | 2023-06-30 | 12 | 955080.0625 |  |  | 12 | 2 | 2 | 1 | 0.94 | 0.94 | 0.06 | 1 | 0.31 |  | 1 | 1 | 1 | Bilateral
88734000000056021 | Play Matters | 1500000 | 0.05 | 2020-01-01 | 2020-08-30 | 2021-08-31 | 7.96 | 8735.2051 |  |  | 6 | 3 | 3 | 1 | 0.9 | 0.9 | 0.1 | 1 | 1 | 0 | 0.8 | 1 | 1 | Foundation
88734000000057017 | Uganda Intergovernmental Fiscal Transfers Program | 500000000 | 0.21 | 2019-05-29 | 2020-08-01 | 2024-07-31 | 14.14 | 7496464 |  | 1.1 | 12 | 13 | 176 | 0.25 | 0.7 | 0.012926 | 0.3 | 0.31293 | 0.44 | 0 | 1 | 1 | 1 | Multi-lateral
88734000000058021 | ABSYR | 2247191 | 1 | 2017-12-01 | 2019-12-31 | 2020-12-31 | 24.99 | 89923.6094 | 6.9 | 12 | 12 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0.9 | 0.1 | 1 | 1 | 1 | Bilateral
88734000000059029 | Resilient Learners, Teachers and Education Systems in South Sudan and Uganda | 2094543.875 | 0.36 | 2018-03-01 | 2020-05-31 | 2022-02-28 | 27.02 | 27806.2852 | 4 | 12 | 12 | 1 | 1 | 1 | 0.75 | 0.75 | 0.25 | 1 | 0.85 | 0.15 | 1 | 1 | 1 | Bilateral
88734000000061069 | Population has optimal access to education | 15602355 | 1 | 2018-01-01 | 2018-12-31 | 2018-12-31 | 11.97 | 1303454.875 | 5.9 | 6 |  | 13 | 12 | 0.75 | 0.98 | 0.79625 | 0.02 | 0.81625 | 0.95 | 0.05 | 1 | 0.99 | 1 | Combination
88734000000063017 | Maintains | 598944.5625 | 0.16 | 2020-01-01 | 2020-06-30 | 2023-06-30 | 5.95 | 16296.7559 |  |  | 6 | 1 | 0 | 1 |  | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | Bilateral